## Tasks
task_id | project_id | task_name | description | assignee | status | priority | deadline | sprint_id
T101 | P001 | Password Login | Implement username/password authentication API | Rahul | In Progress | High | 2026-10-05 | S1
T102 | P001 | OTP Login | Implement OTP-based authentication | Rahul | In Progress | High | 2026-10-10 | S1
T103 | P001 | Product Catalog UI | Build product listing and search UI | Sadaf | Not Started | Medium | 2026-10-12 | S1
T104 | P001 | Cart Module | Implement add/remove/update cart functionality | Sadaf | Not Started | Medium | 2026-10-15 | S2
T105 | P001 | Payment API | Integrate payment provider and payment status API | Rahul | Not Started | High | 2026-10-18 | S2
T106 | P001 | Authentication QA | Test password and OTP authentication | Priya | In Progress | High | 2026-10-09 | S1
T107 | P001 | Deployment Pipeline | Set up CI/CD pipeline for staging | Arjun | Not Started | Medium | 2026-10-16 | S2